## Slide 1: Project Management
Notes: Owner: Doina

## Slide 2: Program Management Team
Engineering Program Managers (EPMs) report to the Engineering Program Management Team. The team is independent of Development, Test and Marketing management.
Reference: https://jive.windriver.com/community/engineering/operations/engineering-program-managers-epm

## Slide 3: Program and Project Management
The Engineering Program Manager (EPM) creates a release in Panorama, facilitate collaboration between Product Management and Engineering leads in defining the plan and milestones for the release
The EPM monitors the release, analyzes and reports on project status and takes corrective action.
https://jive.windriver.com/community/engineering/operations/engineering-program-managers-epm/overview
Notes: EPM Responsibilities: https://jive.windriver.com/docs/DOC-74014
EPM User Guide: https://jive.windriver.com/docs/DOC-75489

## Slide 4: Program Management Tool
Panorama is the Wind River program / release management tool.
Releases are created in Panorama. Based on the Release Type, checklists are defined. These are referred to as PDLC Phase Exit Review checklists that are associated with activities and deliverables
Each item in a checklist has a performer and approver.
Panorama tracks all that has to be done for a release, including
  Planning
  Content
  Development
  Defect tracking
  Testing
  Launching
  Status Reporting
  Issues/Risks/Actions/Program Change Requests
Notes: Panorama:
SR0640: http://panorama.wrs.com/#/release/view/3050/
SR0650: http://panorama.wrs.com/#/release/view/3167/
Jira Dashboards:
SR0640: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20409
SR0650: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20904#

## Slide 5: Management Reviews
Programs have weekly meetings with management leads, to monitor program status, metrics, and quality.
Reviews utilize
  Jira Dashboards
  Panorama
Notes: Panorama:
SR0640: http://panorama.wrs.com/#/release/view/3050/
SR0650: http://panorama.wrs.com/#/release/view/3167/
Jira Dashboards:
SR0640: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20409
SR0650: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20904#
Weekly meetings: Tuesday 6:30 AM PDT / 9:30 AM EDT / 9:30 PM CDT
Minutes:
2020: https://jive.windriver.com/community/engineering/vx7-engineering/vx7-leads-meeting-minutes-2020/content

## Slide 6: Quality Metrics
Defects are reviewed continuously to ensure traction
  Release criteria states no Priority 1 defects at release.
  Any Priority 2 defects must be approved by the Product Manager and Customer Support Team.
Testing results are monitored to ensure that criteria are met
  Nightly results above 95%
  Release test Pass above 95%
  All Domain Pass rate above 90%
Performance and Footprint measurements
  Monitored throughout the program. Test results stored in git
All static analysis defects fixed to ensure adherence to Coverity Integrity Level 3.
Notes: Performance and Footprint
[Native] http://git.wrs.com/cgit/projects/wassp-repos/testcases/vxworks7/tree/system/PerformanceTest/testReport/release/SR0640/SR0640_performance_native.md
[Helix] http://git.wr
s.com/cgit/projects/wassp-repos/testcases/vxworks7/tree/system/PerformanceTest/testReport/release/SR0640/SR0640_performance_helix.md
Release Criteria: https://jive.windriver.com/docs/DOC-69849
LTAF:
Native:http://pek-lpgtest3.wrs.com/ltaf/nightly_results.php?releasename=vx7-integration-helix&clearfilter=true&tf_tr_kf15=helix&tf_tr_whentostart=2020-04-16
Helix: http://pek-lpgtest3.wrs.com/ltaf/nightly_results.php?releasename=vx7-integration-helix&clearfilter=true&tf_tr_kf15=helix&tf_tr_whentostart=2020-04-15

## Slide 7: Risk and Issue Management
Program level risks and issues are filed through Panorama.
Once a risk is identified, the EPM is responsible for creating the risk record, discussing the risk with stakeholders and getting their assessment, and tracking the risk.
Risk information includes: priority, status, owner, mitigation, and contingencies.
If a risk is met (trigger is Due Date), it becomes an issue. The EPM creates an issue. The EPM is responsible for identifying who can resolve the issue. The EPM closes an issue when it is resolved.
https://jive.windriver.com/docs/DOC-84027
Notes: https://jive.windriver.com/docs/DOC-84027
Panorama:
SR0640: http://panorama.wrs.com/#/release/view/3050/
SR0650: http://panorama.wrs.com/#/release/view/3167/
Jira Dashboards:
SR0640: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20409
SR0650: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20904#

## Slide 8: Document and Record Storage
Features, User Stories, Defects, Enhancement Requests, Risks, Issues, Change requests, are maintained in the Jira databases.
Release checklists are kept in Panorama
Artifacts can be stored in Jive, git.
Product code is kept under CM
  VxWorks 6.9.x in Clearcase
  VxWorks 7 in Git
Tests and test results are kept in a repository designated by the test team - LTAF
Notes: LTAF:
Native:http://pek-lpgtest3.wrs.com/ltaf/nightly_results.php?releasename=vx7-integration-helix&clearfilter=true&tf_tr_kf15=helix&tf_tr_whentostart=2020-04-16
Helix: http://pek-lpgtest3.wrs.com/ltaf/nightly_results.php?releasename=vx7-integration-helix&clearfilter=true&tf_tr_kf15=helix&tf_tr_whentostart=2020-04-15

## Slide 9: Program Change Requests
Program Change Requests (PCRs) are filed through Panorama.
PCRs notify stakeholders of a change. Stakeholders must agree to and sign off on a change before it can be approved.
All post POR changes require a PCR
https://jive.windriver.com/docs/DOC-84024
Notes: Panorama:
SR0640: http://panorama.wrs.com/#/release/view/3050/
SR0650: http://panorama.wrs.com/#/release/view/3167/
Jira Dashboards:
SR0640: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20409
SR0650: https://jira.wrs.com/secure/Dashboard.jspa?selectPageId=20904#

## Slide 10: Export, IP
Notes: Owner: Doina

## Slide 11: Export Classification
The Export Classification Policy requires Engineering Program Managers to submit an export encryption form to the Export Compliance Manager for each program. Each release going to customers must have an export form.
Artifacts are captured in the Panorama checklists as sign off
The Export group provides training in the export classification process.
https://jive.windriver.com/docs/DOC-74067
Notes: Global Trade Compliance (Export / Import) : https://jive.windriver.com/community/corporate/compliance-export-import

## Slide 12: Intellectual Property, 3rd party SW
All engineers modifying code in a release attend IP training and must pass a test
IP training is available here https://jive.windriver.com/docs/DOC-74671
Use of 3rd party SW (proprietary and open source) subject to the following:
  Each use disclosed for a given release prior to being integrated into the product
  A license must be identified for each software use that grants the company the required rights
  Designated list of acceptable and prohibited open source licenses
All third party IP included in a release is cleared by the IP review group prior to distribution
Intellectual Property group: https://jive.windriver.com/groups/intellectual-property-group
Disclosures are made in the IP Portal: http://ip.wrs.com/Disclosurelist/tabid/80/Default.aspx