## Slide 1: PDLC / PMO Training / Overview
V7 April 2020
Corporate Overview
Neill Allen - Product Operations

## Slide 2: PDLC / PMO Training / Overview Sections Covered
PDLC Fundamentals
  PDLC Process
  Program Management Office (PMO)
  PDLC Team
Key Techniques Used within the PDLC
Key Roles and Team Member Responsibilities
Governance and Communication Flow

## Slide 3: PDLC / PMO Training / Overview Standardized Product Development Lifecycle (PDLC)
High-Level Description
The Wind River Product Development Life Cycle (PDLC) is a Business Framework and Governance Process for creating and releasing Wind River products to the Markets/Customers we serve.
Goal of the PDLC
Ensure Wind River is achieving the best Return on Investment (ROI) across the product portfolio
Investment & Planning
Definition & Building
Monitoring & Maintenance
Active
Product Line
Release
Launch
Release
Define
Release
RTO
Define
Program
Propose
Program
Live
Prepare for
EOL
Plan
Program
Program
Plan
Release
Propose
Release
Dev-Test
Release
Legacy
EOL
GA
RTO
PER
Released
PDLC Program
Change
Live
In-Review
Test
Program
Changes to Business Model, Strategy or Pricing
PER
PER
PER
PER

## Slide 4: PDLC / PMO Training / Overview Standardized PDLC – Anatomy
PDLC Life Cycle Phases:
  A phase is a logical set of activities within the product Life Cycle. The end of a phase is a milestone that enables the product and supporting teams to assess current status of an in-flight program
  All Product Releases are visible in the PDLC
Phase Reviews:
  Designed all Products from Major Releases to Service Packs with processes optimized for each
  Review & approve evidence (artifacts) that work is complete, enabling the release to continue through the PDLC
  Assessing key risks of release and readiness among key supporting functions
  Level setting between Supporting Functions, Exec Mgt. (as needed) and Product Team(s)
  Support historical analysis, metrics, internal/external audits, and release assessment
PDLC Evidence (Artifacts):
  Artifacts are evidence provided of activities completed within a phase. They provide an objective view of program status
Phase X
Phase 1
Phase 2
Key Milestone

## Slide 5: Program Phases
The Program defines a product and a series of product releases
All Business and product strategy are defined in the Program
Programs may be modified as new release and business needs arise

## Slide 6: PDLC / PMO Training / Overview PDLC – Plan-Program Phase Synopsys
Plan-Program
Propose-Program
Define-Program
Test-Program
Technique/s Available:
Investment Proposals, Portfolio Balancing MVP Validation of New Market or Product opportunity
What Happens:
Product Division performs Due Diligence on a New Market or Product opportunity
Development of Proposal, Plan the Pitch for New funding and/or Portfolio Rebalancing
What’s Delivered:
Understand of TAM and SAM
Completed Business Plan
High level Technical and Market Feasibility
Competitive Analysis
Formal Proposal/Fund Raising Pitch
Sample Questions to Consider:
Is there a Market for this new offering?
How big is the TAM and SAM ?
What’s the Problem that needs to be Solved?...Is it Pervasive, and is there a willingness to pay?
Do we have the Expertise internally?
Does it Support/Drive our Strategy?
Phase Execution
Process Owner: PMO
Product Owner: Product Manager
Support Team: Exec Team
Phase Purpose: Review Due Diligence performed by the Product team i.e. Business/Investment Requirements, Strategic Alignment, High-Level Requirements etc... Approval at the Plan Phase means that the opportunity can move to the Proposal Phase.

## Slide 7: PDLC / PMO Training / Overview PDLC – Propose-Program Phase Synopsys
Technique/s Available:
Agile Planning
Minimum Viable Product (MVP)
Customer Validation, Collaborative Development
What Happens:
High-level Product Releases/Backlog Defined
Funding Approved/Adjusted
MVP Analysis and Execution
Phase Exit Deliverables
What’s Delivered:
Roadmap Deliverables scoped (Initial Release)
Agile Release Backlogs/User Stories/Release Plan
Funding Approvals (Development and PDLC)
Customer Validation/POC Opportuniites, MVP based funding as appropriate
Updated Corporate Roadmap as needed
Sample Questions to Consider:
How does the Program fit with Wind River and Business Unit Strategy? (Customer, Business, and what’s needed Internally)
Are all Functions sufficiently prepared for and committed to the release schedule?
What are the Key Risks that we foresee in executing this program and do we know how to mitigate?
Phase Execution
Process Owner: PMO
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Approval at the Propose phase means that the product division has committed to investing in the development of the release. The subsequent phase, Define, is where the detailed cross-functional planning occurs for the program..
Proposal Approval
Plan-Program
Propose-Program
Define-Program
Test-Program

## Slide 8: PDLC / PMO Training / Overview PDLC – Define-Program Phase Synopsys
Technique/s Available:
Agile Planning
Minimum Viable Product (MVP)
Customer Validation, Collaborative Development
What Happens:
Product Releases Defined
Funding Approved/Adjusted
MVP Analysis and Execution
Phase Exit Deliverables
What’s Delivered:
Roadmap Deliverables scoped
Agile Release Backlogs and User Stories Defined
Funding approvals
Customer Validation/EAR and funding as appropriate
Updated Corporate Roadmap as needed
Sample Questions to Consider:
Do we understand the Product Requirements? (Customer, Business, and what’s needed Internally)
Are all Functions sufficiently prepared and committed to the release schedule?
What are the Key Risks that we foresee in executing this program…?
Do we have our PDLC Team, Pricing. Training Strategy outlined/identified ?
Phase Execution
Process Owner: PMO
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Approval at the Define phase means that Wind River has committed across all functions to support the product program of releases
Plan-Program
Propose-Program
Define-Program
Test-Program

## Slide 9: PDLC / PMO Training / Overview PDLC – Test-Program Phase Synopsys
Technique/s Available:
Agile Development
What Happens:
Agile requirements ready to begin development
Business support such as product codes and comm-spec information communicated
What’s Delivered:
Trade evaluation of the Program Risk Level defined
Finalized Supporting Function Plans (Marketing, Tech Pubs, etc.)
Updated Corporate Roadmap
Sample Questions to Consider:
Have the product requirements changed since the initial requirements were defined?
Has the business justification for the program changed?
Are plans in place for all initial release activities?
Are resources committed for the initial planned release activities?
Phase Execution
Process Owner: PMO
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Certifies that development activity is ready to start and all supporting functions are prepared for the coming sequence of releases
Plan-Program
Propose-Program
Define-Program
Test-Program

## Slide 10: Release Phases
All releases follow the definitions at the Program Level
All release types are supported in a Program
Release checklists are created as the releases are created

## Slide 11: PDLC / PMO Training / Overview PDLC – Plan-Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Technique/s Available:
Agile and CI/CD development
What Happens:
Release content and proposed dates defined
Resources adjusted if necessary
Release defined in the Release Tracking and Engineering Requirements tools
What’s Delivered:
Technical ability to begin development
Resources available match skills necessary to complete the release
Sample Questions to Consider:
Are the requirements clearly defined and understood?
Do we have the Expertise internally and are the skill sets available for this release?
Phase Execution
Process Owner: EPM
Product Owner: Product Manager
Support Team: Engineering
Phase Purpose: Approval at the Plan Phase means there are sufficient requirements defined such that the release can move to the Proposal Phase.

## Slide 12: PDLC / PMO Training / Overview PDLC – Propose-Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Technique/s Available:
Agile Planning
What Happens:
Requirements Backlog Reviewed
Team commits to release schedule
Phase Exit Deliverables
What’s Delivered:
Release introduced to supporting functions
Release content and deliverables defined and agreed to by the engineering team
Agile Release Backlogs/User Stories/Release Plan
Updated Release Tracking Tool phases & dates
Sample Questions to Consider:
Have the proposed release phase dates been agreed to?
Are all Functions sufficiently prepared for and committed to the release schedule?
What are the Key Risks that we foresee in executing this release and do we know how to mitigate?
Phase Execution
Process Owner: EPM
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Approval at the Propose phase means that engineering has committed to the development of the release. The subsequent phase, Define, is where the detailed planning occurs for the release.
Proposal Approval

## Slide 13: PDLC / PMO Training / Overview PDLC – Define-Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Development Approval
Technique/s Available:
Agile Planning,
Minimum Viable Product (MVP) as needed
What Happens:
Release Introduction to PMO
All Release parameters defined
Release requirements on supporting functions defined via the release tracking tool
Phase Exit Deliverables
What’s Delivered:
Updated Release Tracking information
Agile Release Backlogs and User Stories completed
Known POC or EAR deliverables and dates defined and documented
Sample Questions to Consider:
Do we understand the Product Requirements?
Are all Functions sufficiently prepared and committed to the release schedule?
What are the Key Risks that we foresee in executing this release?
Do we have our PDLC Team, Pricing. Training Strategy outlined/identified at the Program Level?
Phase Execution
Process Owner: EPM
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Approval at the Define phase means that Wind River has committed across all functions to develop the product.
Proposal Approval

## Slide 14: PDLC / PMO Training / Overview PDLC – Development & Test Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Technique/s Available:
Agile Development
What Happens:
Agile Sprints (software development and test)
Detailed RTO, GA & Launch Planning
Early Access Release Readiness (EAR)
What’s Delivered:
Finalized Supporting Function Plans (Marketing, Tech Pubs, etc.)
POCs/EARs
Agile Sprint Planning, Groomed Backlog, Pivots as needed
Final Trade approval as needed
Sample Questions to Consider:
Have the product requirements changed since the initial requirements were defined?
Are plans in place for all launch activities?
Are resources committed for all planned launch activities, training, etc.?
Have all IP, Export and related external requirements been completed
Phase Execution
Process Owner: EPM
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: Certifies that development activity has been completed, as evidenced by completion of all features to success criteria. The PMO is notified of the result.
Early Access Release (EAR)
Development Approval
Proposal Approval

## Slide 15: PDLC / PMO Training / Overview PDLC – Launch-Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Development Approval
Technique/s Available:
Transition new products from Development & Test to General Availability (GA)
What Happens:
Launch Execution
RTO & GA Milestones Completed
Release Operations Completed
What’s Delivered:
Quality
Documentation
Launch Collateral and Training
Business Systems (IT) Ready
Orderable/Sellable Product
Sample Questions to Consider:
Has the product met the success criteria established at the beginning of the program (quality, performance, etc.)?
Has all training (field technical, sales, customer) been completed?
Have all launch activities been completed?
Are all internal systems (Oracle, Sales Force) ready for the new product?
Phase Execution
Process Owner: Product Manager / EPM / PMO
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: The Launch phase exit review is conducted by the PDLC Review Board. It is a major checkpoint where the company commits to general availability of the product(s).
Launch PER
Early Access Release (EAR)
Proposal Approval
RTO GA

## Slide 16: PDLC / PMO Training / Overview PDLC – Sustain-Release Phase Synopsys
Plan
Propose
Define
Dev/Test
Launch
Sustain
PDLC
Technique/s Available:
Wind River Support & Continuous Improvement
What Happens:
Customer Satisfaction / Loyalty Reporting
EOL Date Planning and Product Lifecycle Updated
Finance and Operations Metrics
What’s Delivered:
EOL Detailed Plan/Execution
Support/Maintenance releases
Reporting of business results; metrics, comparison to plan
Updated Customer Ed Courses, Demos etc.
Documentation notified to Remove/Remain
Sample Questions Consider:
Have customers been informed ahead of time of the coming transition and options for support?
Have newer products or versions been adopted?
How long has the product been available?
Phase Execution
Process Owner: PMO
Product Owner: Product Manager
Support Team: PDLC Team
Phase Purpose: To review all products Post release and in the Sales Lifecycle to determine when the product/s should transition to End of Life
End of Life (EOL)
Development Approval
Early Access Release (EAR)
Launch PER
Proposal Approval

## Slide 17: PDLC / PMO Training / Overview PDLC – Hierarchy Product Model
Active
Product Line
Release 1 – Major 1.0
Launch
Release
Define
Release
RTO
Release 2 – Update Pack 1.01
Define
Program
Propose
Program
Live
Prepare for
EOL
Plan
Program
Program
Plan
Release
Propose
Release
Dev-Test
Release
Define
Release
Dev-Test
Release
Launch
Release
Legacy
EOL
Release 3 – Minor 1.1
RTO
GA
GA
RTO
PER
Launch
Release
Define
Release
RTO
Plan
Release
Propose
Release
Dev-Test
GA
RTO
Legend
PER : Phase Exit Review (PDLC)
<PDLC Phase>-Program : Overarching Program Checklist
<PDLC Phase>-Release : Release Specific Checklist
– Project
Active Project
Released
Released
Released
Completed
PDLC Program
Change
Release 5 – Concept
Define
Release
RTO
Plan
Release
Propose
Release
Dev-Test
POC
Released
Complete
Live
In-Review
Test
Program
Changes to Business Model, Strategy or Pricing
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
PER
RTO
EOL
Notes: 1/5/2018 (SJL)
Moved complete gate prior to completed state for project and POC
QUESTION: Should Project just have Active and completed states?
QUESTION: Should POC have different states?
ACTION: Test Program phase needs to be in more slides?

## Slide 18: PDLC / PMO Training / Overview Sections Covered
PDLC Fundamentals
  PDLC Process
  Program Management Office (PMO)
  PDLC Team
Key Techniques Used within the PDLC
Key Roles and Team Member Responsibilities
Governance and Communication Flow

## Slide 19: PDLC / PMO Training / Overview Program Management Office (PMO)
Charter/Key Functions…
  Product Portfolio Management and Focal Point of all Portfolio Investments
  Oversight and Cross-Functional coordination of ALL Programs/Products throughout PDLC
  Ensures PDLC compliance and consistent practices across multiple product lines/releases
  Work with Product Divisions, Exec Team, and Supporting Functions to escalate/resolve issues, mitigate risks, and move roadblocks as needed to ensure all programs are on track
  Build metrics on product development effectiveness to ensure PDLC is lean & efficient and efficient Process
  Provides a repository of Program Information, Dashboards, Product Release Policies, and Templates
  Train; Evangelize; Improve and adapt the process
PMO Manages the entire “Business Process” of taking products to market…
$Success$ = (Investment + Planning + Development + Marketing + Sales)
PDLC Team
Notes: 4 Ps = Product Price Promotion & Place

## Slide 20: PDLC / PMO Training / Overview Sections Covered
PDLC Fundamentals
  PDLC Process
  Program Management Office (PMO)
  PDLC Team
Key Techniques Used within the PDLC
Key Roles and Team Member Responsibilities
Governance and Communication Flow

## Slide 21: PDLC / PMO Training / Overview PDLC Team
Team Charter
  PMO Owns and Drives the Team
  Ensure Organization is Ready, Willing and Able to support All Releases
  Continuously improve processes to ensure efficiency and repeatability
  Manage Cross-functional Dependencies
  Identify risks and develop mitigation plans
  Escalate and Triage Issues
Team Structure | 
PMO/Product Operations | Field/PRT
Product Management | Intellectual Property
Alliances | Legal
Corporate Marketing | Online Support
Customer Support | Professional Services
Education/Training | Quality
Engineering Operations | Technical Publications
Trade Compliance | Deal Desk
Key Responsibilities
  Represent their Functional or Product Area (FPA)
    Provide input to the PDLC Team on program related activities
    Inform their teams of PDLC activities, progress, etc.
  Identify, prepare, and manage deliverables their team must have in place to support the PDLC effort
  Improve processes within their FPA
Goals
Standard process across all products
Efficient cross-communication on all releases
Deliver releases as efficiently as possible
Hold one another accountable – One Team

## Slide 22
PDLC / PMO Training / Overview PMO/PDLC Team - How it works within the PDLC
Propose
Product Operations/PMO:
  Governs process and runs the PDLC Team to ensure all phase gates and milestones are on track with their respective deliverables
GTM Team:
  All Supporting Functions represented on PDLC Team - Ensuring deliverables are completed-to-plan to support the product throughout the PDLC
  Forum for Collaboration and Communication across all work streams
  Identify Risks, and as needed Escalate Issues to keep product releases on track
Define
Multiple Work Streams running in parallel for each of the Supporting Functions
Communication, Collaboration, Monitoring, and Visibility Throughout PDLC
Launch
Sustain
In-Flight Snapshot – PDLC Work Streams
Marketing
Legal
Support
Engineering/Eng. Ops
Quality
Technical Pubs
Product Operations / PMO
PDLC Team – Dev Phase

## Slide 23: PDLC / PMO Training / Overview Sections Covered
Origin and Background
PDLC Fundamentals
Key Techniques Used within PDLC
Key Roles and Team Member Responsibilities
Governance and Communication Flow

## Slide 24
Define-Release
Develop-Test Release
Propose-Program
Launch-Release
Investment & Release
Investment Proposals, Portfolio Balancing, ZBB, AOP
Gate 0
Gate 1
Gate 2
Customer Validation
Requirement & Release Planning
Product Definition
Agile Development
Efficient, Collaborative Development
WIND RIVER
New Product Introduction
Go-To-Market
Plan-Program
Key PDLC Techniques
PDLC / PMO Training / Overview Techniques Used in the PDLC – Overview
Key Elements (PPM)
Investment Planning
Fund Raising
Portfolio Management
Overall Product Definition
Key Elements
Release Definition
Requirements Validation
Key Elements (AGILE)
Efficient Product Development
Agile sprint controlled development cycles
Key Elements
Support Organizational Readiness to bring New Products & Features to Market for Major releases
Support Knowledge Transfer and Communication to Downstream Teams

## Slide 25: PDLC / PMO Training / Overview Sections Covered
Origin and Background
PDLC Fundamentals
Key Techniques Used within PDLC
Key Roles and Team Member Responsibilities
  “A Day in the Life” PDLC
Governance and Communication Flow

## Slide 26
PDLC / PMO Training / Overview Key Roles and Responsibilities
Product Manager - Synopsys
  Research/Identify Market/Customer Needs
    Problem to be Solved (The Why)
    Target Market (The Who)
  Prepare Business Justification/Case
  The 4 “P”s (Price, Product, Promotion & Place)
    Product Offering (The What)
    Pricing and Pricing Strategy
    PDLC & Release Strategy
  Drive Engineering/Development Investments for New/Ongoing Products
    Participating in Agile Scrum meetings as needed
    Available to answer questions from Engineering
    Prioritization activities and Backlog Grooming as needed
  Driving all aspects of the “Product” through the PDLC
    Actively Participating in the PDLC Team and release readiness
  Product Introduction/Launch
    Responsible for preparing Sales and Marketing Collateral
Responsible/Accountable
Doesn’t mean the Product Manager has to DO everything, they need to make sure that it’s done correctly, delivers value to the customer and drives the business….

## Slide 27
PDLC / PMO Training / Overview Key Roles and Responsibilities
PMO - Key Responsibilities
  Oversight and Cross-Functional coordination of ALL Programs/Products throughout the PDLC to ensure products are moving efficiently through the process
  Ensures PDLC compliance and consistent practices across multiple product lines/releases
  Information HUB - Work with Product Mgrs., Exec Team, and Supporting Functions to escalate/resolve issues, mitigate risks, and move roadblocks as needed to ensure all programs are on track
  Provides a repository of Program Information, Dashboards, Product Release Policies, and Templates
  Train; Evangelize; Improve and adapt the process
PMO Coordinates all Releases moving through the PDLC – Consultative at times, Drive when needed, support always

## Slide 28
PDLC / PMO Training / Overview Key Roles and Responsibilities
Engineering Program Manager (EPM) - Key Responsibilities
  Owns and Drives the Engineering Processes
  Builds and Delivers the Product as Specified by the Product Manager, on schedule, and High Quality
  Ensures Engineering PDLC Activities, Deliverables, and Evidence are completed and delivered as planned and on schedule
  Works with the Product Manager and PMO when and if schedules need to shift or adjust

## Slide 29: PDLC / PMO Training / Overview Sections Covered
PDLC Fundamentals
Key Techniques Used within PDLC
Key Roles and Team Member Responsibilities
  Releases and Responsibilities
Governance and Communication Flow

## Slide 30: Release Type Definitions
Release Type | High-Level Definition | Impact
Major | New product or major functional changes Breaks backward compatibility API / Behavior changes | Internal Impact: Marketing, Finance, Sales Readiness, Pricing, CSO,FEO, Export, IP, Legal, Engineering Program Manager, Release & Production, Ex-ops, Tech Pub, Training Customer Impact: Application changes required to adopt the release Training / documentation on new functionality Possible migration challenges
Minor | Major enhancements and / or new features Limited API or behavior changes | Internal Impact: Marketing, Finance, Sales Readiness, Pricing, CSO,FEO, Export, IP, Legal, Engineering Program Manager, Release & Production, Ex-ops, Tech Pub Customer Impact: Training / documentation on new functionality
Update Pack | Minor enhancements, new features and / or bug fixes Fully backwards compatible | Internal Impact: Marketing, Finance, Sales Readiness, Pricing, CSO, FEO, Export, IP, Legal, Engineering Program Manager, Release & Production, Ex-ops, Tech Pub Customer Impact: Documentation on new functionality and changes
Service Pack | Bug Fixes Only No New Features or Enhancements Fully backwards compatible | Internal Impact: Export, Engineering Program Manager, Release & Production, CSO, FEO, Tech Pub Customer Impact: Defect resolution documentation

## Slide 31
Activities/Deliverables Required by Product Mgt., Engineering Program Mgt., and PMO for each PDLC Phase
PDLC / PMO Training / Overview “A Day in the Life” Release Responsibility Summary
Role/ Function | PDLC Program Phases |  |  |  | 
 | Plan-Program | Propose-Program | Define-Program | Test-Program | 
Product Mgr. (PdM) | Creates Plan for New Product/Major Product Updates. Supplies Checklist Evidence Presents the Business Case Business Case Approved |  | Follows Define Phase Checklist Populates Evidence in Panorama Receives Approvals | Follows Dev/Test Checklist Populates Evidence in Panorama Receives Approvals | 
Engineering PM (ePM) |  |  |  |  | 
PMO | Reviews Program, Consults with Product Manager on overall release plan Reviews Program date commitments and Checklists |  | Reviews checklists and deliverables Communicates program concepts through the PDLC team | Reviews checklists and deliverables | 
Supporting Functions | Participates in the PDLC Review of the Product Proposal |  | Participates/Knowledge Transfer Readies their Teams Defines their Deliverables | Participates/Knowledge Transfer Builds and Completes their deliverables | 
Milestones / Process Steps | Business Case Developed, Proposed and Approved PER Milestone completed |  | Business aspects defined PER Milestone completed | Initial order processing and product support functions defined PER Milestone completed | 

## Slide 32
Activities/Deliverables Required by Product Mgt., Engineering Program Mgt., and PMO for each PDLC Phase
PDLC / PMO Training / Overview “A Day in the Life” Release Responsibility Summary
Role/ Function | PDLC Phases |  |  |  | 
 | Plan | Propose | Define | Develop/Test | Launch
Product Mgr. (PdM) | Reviews requirements backlog Supplies Checklist Evidence |  | Follows Define Phase Checklist Answers Questions in Release Tracking to finalize checklists Populates evidence in Panorama Receives Approvals | Follows Dev/Test Checklist Populates Evidence in Panorama Receives Approvals | Follows Launch Checklist Populates Evidence in Panorama Receives Approvals
Engineering PM (ePM) | Creates Release in Panorama RTO / GA Dates Proposed |  | Answers Release Questions in Panorama Manages Release Tracking | Manages Development Populates RTO/GA Milestone Evidence in Release Tracking Coordinates with Release Team Go/No-Go Approvals | Verifies release completion Populates evidence and archives release information
PMO | Reviews Release, Consults with Product Manager on release plan Reviews release & checklists in Panorama |  | Monitors PER status Holds PDLC meetings reviewing all milestones | Monitors PER status Holds PDLC meetings reviewing all milestones | Monitors PER status Holds PDLC meetings reviewing release completion Sends release notifications
Supporting Functions |  |  | Readies their Teams Reviews their Deliverables | Builds and Completes their deliverables | Participates in PDLC Review Ready to sell & support product
Milestones / Process Steps | Release schedule approved Phase Exit Review (PER) Milestone Completed |  | PER Dates defined Phase Exit Review (PER) Milestone Completed | Phase Exit Review (PER) Milestone Completed | Phase Exit Review (PER) Milestone Completed

## Slide 33: PDLC / PMO Training / Overview Sections Covered
Origin and Background
PDLC Fundamentals
Key Techniques Used within PDLC
Key Roles and Team Member Responsibilities
Communication and Governance Flow

## Slide 34
Product Managers
  Communicates with PMO to plan and coordinate product releases
  Responsible for communication with all PDLC Team members and supporting functions
  Articulates Product Strategy and success criteria
Program Management Office
  PMO, works with the Product Manager and Engineering Program Manager, communicates with all supporting functions to ensure all are ready and able to support the release as scheduled
  Communicates overall status of all releases in-flight
Engineering Program Managers
  Communicates the Engineering Schedule, Status and Quality of all in-flight Releases
PDLC Team and Supporting Functions
  Must communicate status of their activities and deliverables in support of the releases in-flight, including any potential delays and/or risks that may have a material impact on the schedule
PDLC / PMO Training / Overview Communication Flow
Program Management Office
Engineering Program Manager
PDLC Team
Product Manager
Product Requirements, Market Timing, Release Plan, Schedule
Product Strategy, Financial Goals, Success Criteria, Overall PDLC Management
Engineering Progress, Schedule Updates, Technology Readiness

## Slide 35: Team Communication
Business & Supporting Functions
Product Manager / Product Owner
Product Management Office (PMO)
Release & Production Customer Support
Alliances Finance
Export Compliance IP Compliance
Marketing Technical Marketing
Field Support Sales Operations
Quality Assurance Deal Desk
Product Readiness (PRT) Legal
Tech Pubs & Training Pricing
Optimize Time & Communication Channels
Product Manager, Product Owner & Engineering Program Manager are a TEAM
Product Strategy Meetings (Product Line)
Requirements & Strategy
Product Manager / Product Owner
Engineering Program Manager
Engineering Manager(s)
System Architect
Technical Publications
Business Functions
Engineering Functions
PDLC Team Meetings
(All Products)
Product Engineering Meetings
(Product )
Technical Engineering
Engineering Team Leads
Engineering Program Manager
Engineering Team

## Slide 36: PDLC / PMO Training / Overview Sections Covered
PDLC Fundamentals
Key Roles and Team Member Responsibilities
Communication and Governance Flow
Tools Overview:
  Jira-Agile
  Panorama
  Delivery+
  Windshare
  Wind River Support Network (WRSN)

## Slide 37: Tools Overview
Tracking & Visibility, Release Management, Documentation
Rally –
  Feature backlog & tracking
Panorama –
  Release management,
  Tracking & reporting
Delivery+
  Release definition
  Product Commercialization
Windshare
  Released product access
Knowledge Library
  Documentation
  Defect posting

## Slide 38: PDLC / PMO Training / Overview Questions

## Slide 39: Program Management Office (PMO)
Neilll Allen - Product Operations