## Sheet1
To declare Plan of Record (POR) for a release, each of the features targetted for the release have to meet below criteria.
For each epic (feature), following fields have to be filled in:
| Technical Feature Owner | Engineering Manager
| PA Owner | Domain Architect
| Acceptance Criteria | PM
| Definition of Done | PM
| Dependencies / Impacts captured (if any) | PA Owner/PM
| Committed Version | Eng. Manager/ Scrum Master
| Scrum Team | Eng. Manager/ Scrum Master
| Marketing | PM or Eng Manager
| Refined Estimates | TFO/Scrum Master
To declare POR at the release level:
All individual epics have to meet the POR criteria
Content has to consist of 80% Product Manamagement requested epics
Product Management has to sign off on the POR content
Post POR, all changes to the content, are tracked via PCR.